## Sheet1
F02-02 Rev. # 9, Nov-07-2025
RECORD TECHNOLOGY & DEVELOPMENT
MANUFACTURING PROCESS
Cust.: | Candu | [5 empty] | RFQ# |  |  | OE # : | 39021 | Job # : | 72713-14
P.O. #: | RT98-88010-PN-R010 |  | Line# | 1 & 2 | Part/DWG # : |  |  | RT-87910-0133-1-GA-0 -It.3 |  |  |  |  | Rev. : | 5
Date: | 2025-09-08 |  |  | Description: |  | Scribing Tool Assembly; Scribing Tool Bit
Delivery required: |  | 2026-08-31 | [7 empty] | Contact: | S.B. | Quantity: | 1 + 1
Insp/Oper. |  | Shop Code |  | Processes | [7 empty] | Date | Remarks / NCR#
|  | P | 10 | M4 High speed Steel" c/w MTR
|  | RT | 20 | Receive; inspect; Identify; HT#
|  | RT | 30 | Cut as required
|  | RT | 40 | Prep; machine as per DWG
|  | RT | 50 | Weld as per DWG using SS312 rod
|  | I | 60 | Inspect c/w M/U Dwg; DIR.
Atlantic HT |  | SC | 70 | Heat treat to Rc 50-60 c/w CofC
|  | RT | 80 | Receive; inspect; Identify;
|  | RT | 90 | Grind as necessary
|  | RT | 100 | Deburr; Clean
|  | RT | 110 | Identify
|  | I | 120 | Inspect c/w M/U Dwg; DIR.
|  | RT | 130 | protect for further Assembly -133 -0130
Created by: |  | Steve | [7 empty] | Approved: | Olivier Daros
Date: |  | 2026-04-16 | [7 empty] | Date: | 2026-04-16
P = Purchase, FI = Free Issued Mat'l, RT = Record to Manufacture, SC = Subcontract, I = Inspect, H = Hold; W = Witness; PI =Packaging Inspection.
Procedures are given as a guideline only and may change depending on material size and machine available.