## Sheet1
F02-02 Rev. # 9, Nov-07-2025
RECORD TECHNOLOGY & DEVELOPMENT
MANUFACTURING PROCESS
Cust.: | Candu | [5 empty] | RFQ# |  |  | OE # : | 39021 | Job # : | 72719
P.O. #: | RT98-88010-PN-R010 |  | Line# | 7 | Part/DWG # : |  |  | RT-88000-70035-066-1-DD-B |  |  |  |  | Rev. : | 0
Date: | 2025-09-08 |  |  | Description: |  | End Fitting Bench Fixture; Bar
Delivery required: |  | 2026-08-31 | [7 empty] | Contact: | S.B. | Quantity: | 2
Insp/Oper. |  | Shop Code |  | Processes | [7 empty] | Date | Remarks / NCR#
|  | P | 10 | C-1018 CRS as per BOM -070 It.3 c/w MTRs
|  | RT | 20 | inspect c/w M/U DWG; DIR; FOD
|  | RT | 30 | Cut as per DWG
|  | RT | 40 | Drill; Tap as per DWG
|  | RT | 50 | Deburr; Clean
|  | RT | 60 | Identify
|  | I | 70 | Inspect c/w M/U DWG; DIR; FOD
|  | RT | 80 | Paint per DWG
|  | RT | 90 | Protect; Store for Assembly
Created by: |  | Steve | [7 empty] | Approved: | Steve
Date: |  | 2026-03-22 | [7 empty] | Date: | 2026-03-22
P = Purchase, FI = Free Issued Mat'l, RT = Record to Manufacture, SC = Subcontract, I = Inspect, H = Hold; W = Witness; PI =Packaging Inspection.
Procedures are given as a guideline only and may change depending on material size and machine available.