## Sheet1
F02-02 Rev. # 9, Nov-07-2025
RECORD TECHNOLOGY & DEVELOPMENT
MANUFACTURING PROCESS
Cust.: | Candu | [5 empty] | RFQ# |  |  | OE # : | 39021 | Job # : | 72717
P.O. #: | RT98-88010-PN-R010 |  | Line# | 5 | Part/DWG # : |  |  | RT-88000-70036-002-1&-2-DD-D |  |  |  |  | Rev. : | 2
Date: | 2025-09-08 |  |  | Description: |  | End Stop Bench (RH) Seet 1 & 2
Delivery required: |  | 2026-08-31 | [7 empty] | Contact: | S.B. | Quantity: | 1
Insp/Oper. |  | Shop Code |  | Processes | [7 empty] | Date | Remarks / NCR#
|  | P | 10 | Material as per Sheet 1 BOM c/w MTR
|  | RT | 20 | Receive; inspect; Identify; HT for each Item when received
|  | RT | 30 | Cut as necessary
|  | RT | 40 | Prep as per DWG
Conrex |  | SC | 50 | Sand Blast to SP6
|  | RT | 60 | Receive; inspect; Identify;
|  | RT | 70 | Weld as per DWG and Notes
Perfection Insp. |  | SC | 80 | Visual Weld Inspect c/w report
|  | RT | 90 | Deburr; Clean
|  | RT | 100 | Identify
|  | I | 110 | Inspect c/w M/U DWG; DIR; FOD
|  | RT | 120 | Prime and Paint as per Note
|  | RT | 130 | Protect; Store for further Assembly
Created by: |  | Steve | [7 empty] | Approved: | Olivier Daros
Date: |  | 2026-03-01 | [7 empty] | Date: | 2026-03-01
P = Purchase, FI = Free Issued Mat'l, RT = Record to Manufacture, SC = Subcontract, I = Inspect, H = Hold; W = Witness; PI =Packaging Inspection.
Procedures are given as a guideline only and may change depending on material size and machine available.