## Sheet1
F02-02 Rev. # 8, Mar-27-2024
RECORD TECHNOLOGY & DEVELOPMENT
MANUFACTURING PROCESS
Cust.: | Candu | [5 empty] | RFQ# |  |  | OE # : | 39021 | Job # : | 72715
P.O. #: | RT98-88010-PN-R010 |  | Line# | 3 | Part/DWG # : |  |  | RT-88000-70059-000-1-GA-E |  |  |  |  | Rev. : | 1
Date: | 2025-09-08 |  |  | Description: |  | Bore Gague & Ring Gauge Cal. Stor Trough
Delivery required: |  | 2026-03-18 | [7 empty] | Contact: | Sanchia Bartley Ndiaye | Quantity: | 2
Insp/Oper. |  | Shop Code |  | Processes | [7 empty] | Date | Remarks / NCR#
McMaster |  | P | 10 | Item2006: Flat Head Socket Cap Screw, 1/4-20x1 (McM# 91253A542) as per BOM c/w Cert (Check Stock)
|  | P | 20 | Item2007: Socket Set Screw, 5/16-18x1/2 (McM# 91375A578) as per BOM c/w Cert (Check Stock)
|  | P | 30 | Loctite N-5000 High Purity Anti-Seize as per DWG (Check Stock; See Note 3)
|  | RT | 40 | Receive or Stock; Inspect; Identify
|  | RT | 50 | Gather All Items as per BOM - Check everything is OK!!
|  | RT | 60 | Assembly as per DWG (See Notes 1 - 3)
|  | RT | 70 | Item0003: Drill & Tap (4x) 1/4-20 UNC ↧ Thru as per DWG (See DWG# RT-88000-70059-003-1-DD-D)
|  | RT | 80 | Drill & Tap (4x) 1/4-20 UNC ↧ .50" as per DWG (See DWG# RT-88000-70059-003-1-DD-D)
|  | RT | 90 | Item0004: Drill & Tap (2x) 1/4-20 UNC ↧ .50" as per DWG (See DWG# RT-88000-70059-004-1-DD-D)
|  | RT | 100 | Deburr; Clean; Identify (L-Etch)
|  | I | 110 | Inspect c/w DIR; FOD (Mark Dim's on DWG)
|  | RT | 120 | Protect; Pack; Identify
|  | RT | 130 | Call for Pick-up; Ship as Req'd
Created by: |  | Hunter Towle | [7 empty] | Approved: | Olivier Daros
Date: |  | 2025-10-10 | [7 empty] | Date: | 2025-10-10
P = Purchase, FI = Free Issued Mat'l, RT = Record to Manufacture, SC = Subcontract, I = Inspect, H = Hold; W = Witness
Procedures are given as a guideline only and may change depending on material size and machine available.